## START HERE
North interchange
UNAPPROVED · fictional source review · no professional decisions or approvals recorded
unique current source versions | unresolved source versions |  | proposed target rows
1 | 0 |  | 2
MANAGEMENT QUESTION
One package spans two scope dimensions.
WHY IT MATTERS |  | NEXT PROFESSIONAL REVIEW · NOT AN APPROVED ACTION
One source-record version has two proposed WBS targets. CAD 120,000 is its whole source value, not an allocation to either target. The target views must not be added together. |  | Confirm both scope connections and obtain an explicit allocation basis before attributing any shared package value to a WBS element. Record professional decisions and separate approval.
Findings and review requests | Browse supplied Owner WBS |  | Follow each source record
Open original source files | Counting and authority
Source-supported multi-target proposals are not professional decisions, approved mappings or child-level financial allocations.
M-P01 appears at both targets. One unique package; do not sum target counts or allocate its CAD 120,000 whole value to children. No source count establishes progress, payment entitlement or project health.

## Findings
Management matter | Significance | Exact review request · not a governed Action | Original evidence route | ← START HERE
One package spans two scope dimensions. | One source-record version has two proposed WBS targets. CAD 120,000 is its whole source value, not an allocation to either target. The target views must not be added together. | Confirm both scope connections and obtain an explicit allocation basis before attributing any shared package value to a WBS element. Record professional decisions and separate approval. | Shared_Trade_Package.csv, row 2; Owner_Scope_Register.csv, rows 2–4.

## Owner WBS
Owner Code | Name | Actual parent | ← START HERE
T01 | North interchange
T01.N | North Station | T01
T01.TR | Trackwork | T01

## Crosswalk
Source record ID | View | Proposed WBS targets | Review state | Revision | Description | Source document | Locator | Whole source amount | Currency | Financial basis / boundary | Original source assertion | Contrary evidence | Recorded engine basis | Stable source version ID | Original file SHA-256 | Professional decision | Whole-version approval | Recorded classification | ← START HERE
M-P01 | package | T01.N; T01.TR | Proposed · unapproved | A | Install trackwork at North Station | Shared_Trade_Package.csv | row 2 | 120000 | CAD | CAD 120000 is the whole shared package source amount. No amount is allocated to either WBS target; values must not be added across targets. | Record ID: M-P01 ¦ Owner Code: ¦ Description: Install trackwork at North Station ¦ Trade: Fictional Transit Works ¦ Area: NS ¦ System: TRK ¦ Start: ¦ Finish: ¦ Amount: 120000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Synthetic source assertion ¦ Basis: CAD 120000 is the whole shared package source amount. No amount is allocated to either WBS target; values must not be added across targets. ¦ Boundary: One package covers North Station and Trackwork, two different scope dimensions. Source-supported connections require professional review and separate approval. No cost allocation, payment certification or reporting-cycle approval is supplied. |  | genuine_multi | MULTI-05-Shared_Trade_Package.csv-M-P01 | fd5b64aec9e60e6ae8aebde0d25b341c3e7b710ad2566ff58d978c7ed6ee4d07 | No professional decision recorded | UNAPPROVED | MAPPED

## Sources
Original file | Source type | SHA-256 | Bytes | Located blocks | ← START HERE
Owner_Scope_Register.csv | Owner WBS | 0a1703961de3b2098e6a3db4096562934f9b9c70ec19a362ce39e287b9e93084 | 141 | 3
Shared_Trade_Package.csv | package | fd5b64aec9e60e6ae8aebde0d25b341c3e7b710ad2566ff58d978c7ed6ee4d07 | 613 | 1

## Measurement
Measure / authority | Value / boundary | ← START HERE
Data | Separately fabricated fictional case; original source bytes retained
Approval | No professional decisions or approvals recorded
Energy and carbon | Not measured
External AI | Not tested; no paid API or external model calls
Counting | Unique source versions and target rows are different populations
Canonical snapshot SHA-256 | 5e79eb956b213428e6352aaac1720c397a7042bd81cd17ef904d4249ece349e4
Actual WBS target | Same shared source record
T01.N North Station | 1
T01.TR Trackwork | 1