## START HERE
Northline data centre
UNAPPROVED · fictional source review · no professional decisions or approvals recorded
unique current source versions | unresolved source versions |  | proposed target rows
8 | 3 |  | 8
MANAGEMENT QUESTION
One switchboard. Two finish dates.
WHY IT MATTERS |  | NEXT PROFESSIONAL REVIEW · NOT AN APPROVED ACTION
Revision A states 21 August 2026; proposed revision B states 4 September 2026. Applicability remains unresolved. This is not an approved delay. |  | Confirm the applicable N-S01 schedule revision through professional review and separate schedule approval; preserve both source assertions.
Findings and review requests | Browse supplied Owner WBS |  | Follow each source record
Open original source files | Counting and authority
Source assertions, engine proposals, professional decisions and separate approvals remain distinct. No professional decisions or approvals recorded.
Source records count once. Targets are separate; shared full values are never child allocations. No source count establishes progress, payment entitlement or project health.

## Findings
Management matter | Significance | Exact review request · not a governed Action | Original evidence route | ← START HERE
One switchboard. Two finish dates. | Revision A states 21 August 2026; proposed revision B states 4 September 2026. Applicability remains unresolved. This is not an approved delay. | Confirm the applicable N-S01 schedule revision through professional review and separate schedule approval; preserve both source assertions. | Activity_Extract_RevA.csv, row 2; Switchgear_Dates_Proposed_RevB.csv, row 2; Review_and_Allocation_Notice.docx, paragraph 3.
Commissioning has dates, but no cost allocation. | The parent electrical allowance is not an independently allocated commissioning amount. Missing cost evidence is not zero cost. | Obtain the commissioning cost allocation and confirm its basis before attributing any parent electrical amount to this scope. | Activity_Extract_RevA.csv, row 3; Budget_Allowances.csv, row 2; Review_and_Allocation_Notice.docx, paragraph 4.
Supply and installation have different boundaries. | N-P01 is parent-level installation, including commissioning. N-P02 is switchboard supply only. Neither supplies a child installation value. | Confirm package inclusions and exclusions before assigning installation scope or value to a child WBS element. | Trade_Package_Register.csv, rows 2–3; Review_and_Allocation_Notice.docx, paragraph 5.
Confirm what the parent allowance represents. | The source assigns N-C01 to Electrical, but the deterministic evidence check flags allowance wording for professional review. The source amount remains an unapproved parent assertion. | Confirm the scope and financial basis of N-C01 before treating the parent allowance as an applicable management amount. | Budget_Allowances.csv, row 2; Review_and_Allocation_Notice.docx, paragraph 4.
A proposed connection still needs a professional decision. | The fictional sources support proposals, not professional acceptance, whole-version approval or payment entitlement. | Review source applicability and proposed connections; record professional decisions separately from mapping approval and payment certification. | Review_and_Allocation_Notice.docx, paragraph 6.

## Owner WBS
Owner Code | Name | Actual parent | ← START HERE
N01 | Northline data centre
N01.A | Building A | N01
N01.A.E | Electrical | N01.A
N01.A.E.SG | Switchgear | N01.A.E
N01.A.E.CX | Electrical commissioning | N01.A.E
N01.A.M | Mechanical | N01.A

## Crosswalk
Source record ID | View | Proposed WBS targets | Review state | Revision | Description | Source document | Locator | Whole source amount | Currency | Financial basis / boundary | Original source assertion | Contrary evidence | Recorded engine basis | Stable source version ID | Original file SHA-256 | Professional decision | Whole-version approval | Recorded classification | ← START HERE
N-S01 | schedule | N01.A.E.SG | Unresolved | A | Install main switchboard | Activity_Extract_RevA.csv | row 2 |  |  | No child allocation inferred | Record ID: N-S01 ¦ Owner Code: N01.A.E.SG ¦ Description: Install main switchboard ¦ Trade: Polar Power ¦ Phase: Systems ¦ Start: 2026-08-03 ¦ Finish: 2026-08-21 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion | Competing source revisions; applicability and separate schedule approval are unresolved. Neither assertion is selected by upload order. | assigned | NORTHLINE-04-Activity_Extract_RevA.csv-N-S01 | e4ece9357b4e9caf76e91141ad437ab7ff14be526573f80a625d24fa10e3a9fb | No professional decision recorded | UNAPPROVED | UNSURE
N-S02 | schedule | N01.A.E.CX | Proposed · unapproved | A | Integrated electrical commissioning | Activity_Extract_RevA.csv | row 3 |  |  | No child allocation inferred | Record ID: N-S02 ¦ Owner Code: N01.A.E.CX ¦ Description: Integrated electrical commissioning ¦ Trade: Polar Power ¦ Phase: Commissioning ¦ Start: 2026-09-07 ¦ Finish: 2026-09-18 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion |  | assigned | NORTHLINE-04-Activity_Extract_RevA.csv-N-S02 | e4ece9357b4e9caf76e91141ad437ab7ff14be526573f80a625d24fa10e3a9fb | No professional decision recorded | UNAPPROVED | MAPPED
N-S03 | schedule | N01.A.M | Proposed · unapproved | A | Install cooling equipment | Activity_Extract_RevA.csv | row 4 |  |  | No child allocation inferred | Record ID: N-S03 ¦ Owner Code: N01.A.M ¦ Description: Install cooling equipment ¦ Trade: Boreal Mechanical ¦ Phase: Systems ¦ Start: 2026-08-03 ¦ Finish: 2026-09-04 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion |  | assigned | NORTHLINE-04-Activity_Extract_RevA.csv-N-S03 | e4ece9357b4e9caf76e91141ad437ab7ff14be526573f80a625d24fa10e3a9fb | No professional decision recorded | UNAPPROVED | MAPPED
N-C01 | cost | N01.A.E | Unresolved | A | Electrical budget allowance; not allocated to child WBS | Budget_Allowances.csv | row 2 | 1800000 | CAD | Parent electrical budget; no commissioning allocation supplied. | Record ID: N-C01 ¦ Owner Code: N01.A.E ¦ Description: Electrical budget allowance; not allocated to child WBS ¦ Trade: Polar Power ¦ Phase: ¦ Start: ¦ Finish: ¦ Amount: 1800000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion ¦ Basis: Parent electrical budget; no commissioning allocation supplied. | Semantic evidence points elsewhere (weak): the text uses reserve / contingency wording, which can also describe a procedure rather than a reserve; this WBS has no such element. The source assignment still decides. | assigned | NORTHLINE-04-Budget_Allowances.csv-N-C01 | a07c0841ee2d5dbfd307cd38858af092102e915a57c7043000dcc7884ad6b663 | No professional decision recorded | UNAPPROVED | UNSURE
N-C02 | cost | N01.A.E.SG | Proposed · unapproved | A | Switchgear supply allowance; included in N-C01, not additive | Budget_Allowances.csv | row 3 | 420000 | CAD | Included in N-C01; source value, not a variance or additional budget. | Record ID: N-C02 ¦ Owner Code: N01.A.E.SG ¦ Description: Switchgear supply allowance; included in N-C01, not additive ¦ Trade: Northstar Switchboards ¦ Phase: ¦ Start: ¦ Finish: ¦ Amount: 420000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion ¦ Basis: Included in N-C01; source value, not a variance or additional budget. |  | assigned | NORTHLINE-04-Budget_Allowances.csv-N-C02 | a07c0841ee2d5dbfd307cd38858af092102e915a57c7043000dcc7884ad6b663 | No professional decision recorded | UNAPPROVED | MAPPED
N-S01 | schedule | N01.A.E.SG | Unresolved | B | Install main switchboard | Switchgear_Dates_Proposed_RevB.csv | row 2 |  |  | No child allocation inferred | Record ID: N-S01 ¦ Owner Code: N01.A.E.SG ¦ Description: Install main switchboard ¦ Trade: Polar Power ¦ Phase: Systems ¦ Start: 2026-08-10 ¦ Finish: 2026-09-04 ¦ Amount: ¦ Currency: ¦ Revision: B ¦ Status: Proposed; applicability unresolved | Competing source revisions; applicability and separate schedule approval are unresolved. Neither assertion is selected by upload order. | assigned | NORTHLINE-04-Switchgear_Dates_Proposed_RevB.csv-N-S01 | 357ab1a5d69b7388bae228dcf1c889c13ef86d10e84e1bd8ea9cc154686ce849 | No professional decision recorded | UNAPPROVED | UNSURE
N-P01 | package | N01.A.E | Proposed · unapproved | A | Electrical installation package | Trade_Package_Register.csv | row 2 |  |  | Covers electrical installation including commissioning; parent scope only. No child value allocation supplied. | Record ID: N-P01 ¦ Owner Code: N01.A.E ¦ Description: Electrical installation package ¦ Trade: Polar Power ¦ Phase: ¦ Start: ¦ Finish: ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion ¦ Boundary: Covers electrical installation including commissioning; parent scope only. No child value allocation supplied. |  | assigned | NORTHLINE-04-Trade_Package_Register.csv-N-P01 | 638cf3c033f4095e37032ce9a032fe65a523db9b18155857289112eb9d972bdc | No professional decision recorded | UNAPPROVED | MAPPED
N-P02 | package | N01.A.E.SG | Proposed · unapproved | A | Switchboard supply package | Trade_Package_Register.csv | row 3 |  |  | Supply only; installation remains in parent package N-P01. No package amount supplied. | Record ID: N-P02 ¦ Owner Code: N01.A.E.SG ¦ Description: Switchboard supply package ¦ Trade: Northstar Switchboards ¦ Phase: ¦ Start: ¦ Finish: ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion ¦ Boundary: Supply only; installation remains in parent package N-P01. No package amount supplied. |  | assigned | NORTHLINE-04-Trade_Package_Register.csv-N-P02 | 638cf3c033f4095e37032ce9a032fe65a523db9b18155857289112eb9d972bdc | No professional decision recorded | UNAPPROVED | MAPPED

## Sources
Original file | Source type | SHA-256 | Bytes | Located blocks | ← START HERE
Activity_Extract_RevA.csv | schedule | e4ece9357b4e9caf76e91141ad437ab7ff14be526573f80a625d24fa10e3a9fb | 430 | 3
Budget_Allowances.csv | cost | a07c0841ee2d5dbfd307cd38858af092102e915a57c7043000dcc7884ad6b663 | 487 | 2
Owner_Scope_Register.csv | Owner WBS | f28a7bcf2894afb76bce449a2585c865755fe086cbbfbd35f50f62fff0573351 | 202 | 6
Review_and_Allocation_Notice.docx | review note | 8285a96c4693112bec5c44a79bc7421ed692dc1a28969d68e0864058876f626f | 1238 | 6
Switchgear_Dates_Proposed_RevB.csv | schedule | 357ab1a5d69b7388bae228dcf1c889c13ef86d10e84e1bd8ea9cc154686ce849 | 215 | 1
Trade_Package_Register.csv | package | 638cf3c033f4095e37032ce9a032fe65a523db9b18155857289112eb9d972bdc | 473 | 2

## Measurement
Measure / authority | Value / boundary | ← START HERE
Data | Separately fabricated fictional case; original source bytes retained
Approval | No professional decisions or approvals recorded
Energy and carbon | Not measured
External AI | Not tested; no paid API or external model calls
Counting | Unique source versions and target rows are different populations
Canonical snapshot SHA-256 | eae008800839134e7bc63960a5004aec26983a0d8bcbfeba1b4d51616c8ebd00
Source view | Unique source versions
schedule | 4
cost | 2
package | 2