## Sheet
Line No | Cost Code | Description of Work | Scheduled Value | Work Completed to Date
101 | 26-13-H1-1 | Medium Voltage Equipment Install - Hall 1 | 445900 | 0
102 | 26-13-H1-2 | Medium Voltage qEuipment Test & commission - Hall 1 | 524900 | 129300
12789 | 26-33-H1-3 | Static UPS Install - Hall 1 | 1071600 | 333500
104 | 26-33-H1-4 | Static UPS Test & commission - Hall 1 | 1077200 | 190200
105 | 26-25-H1-5 | Power track Install - Hall 1 | 1731900 | 0
106 | 26-25-H1-6 | Power track Test & commission - Hall 1 | 1735600 | 0
107 | 23-81-H1-7 | CRAH units Install - Hall 1 | 1657100 | 0
108 | 23-81-H1-8 | CRAH units Test & commission - Hall 1 | 1110600 | 1400
109 | 23-21-H1-9 | CRAH units Test & commission - Hall 1 | 1445500 | 0
110 | 23-21-H1-10 | Chilled water piping Test & commission - Hall 1 | 1826300 | 0
111 | 25-10-H1-11 | Controls system Install - Hall 1 | 1459600 | 856600
112 | 25-10-H1-12 | Controls system Test & commission - Hall 1 | 1521900 | 183300
113 | 25-30-H1-13 | PQ meters Install - Hall 1 | 1082600 | 576300
114 | 25-30-H1-14 | PQ meters Test & commission - Hall 1 | 890900 | 0
115 | 26-13-H2-15 | Medium Voltage Equipment Install - Hall 2 | 540400 | 0
116 | 26-13-H2-16 | Medium Voltage Equipment Test & commission - Hall 2 | 1178500 | 76300
117 | 26-33-H2-17 | Static UPS Install - Hall 2 | 378400 | 282800
118 | 26-33-H2-18 | Static UPS Test & commission - Hall 2 | 476300 | 0
119 | 26-25-H2-19 | Power track Install - Hall 2 | 1307600 | 0
120 | 26-25-H2-20 | Power track Test & commission - Hall 2 | 2490700 | 0
121 | 23-81-H2-21 | CRAH units Install - Hall 2 | 257900 | 97800
122 | 23-81-H2-22 | CRAH units Test & commission - Hall 2 | 390000 | 97500
12790 | 23-21-H2-23 | Chilled water piping Install - Hall 2 | 2830000 | 0
124 | 23-21-H2-24 | Chilled water piping Test & commission - Hall 2 | 1787300 | 0
125 | 25-10-H2-25 | Controls system Install - Hall 2 | 2192800 | 0
12792 | 25-10-H2-26 | Controls system Test & commission - Hall 2 | 2721400 | 773300
127 | 25-30-H2-27 | PQ meters Install - Hall 2 | 754000 | 0
128 | 25-30-H2-28 | PQ meters Test & commission - Hall 2 | 1292200 | 0
129 | 26-13-H3-29 | Medium Voltage Equipment Install - Hall 3 | 1675800 | 576300
130 | 26-13-H3-30 | Medium Voltage Equipment Test & commission - Hall 3 | 2516300 | 1502900
12791 | 26-33-H3-31 | Static UPS Install - Hall 3 | 325500 | 236800
132 | 26-33-H3-32 | Static UPS Test & commission - Hall 3 | 146300 | 31600
133 | 26-25-H3-33 | Power track Install - Hall 3 | 1969700 | 555400
134 | 26-25-H3-34 | Power track Test & commission - Hall 3 | 2169600 | 0
135 | 23-81-H3-35 | CRAH units Install - Hall 3 | 1143500 | 356000
136 | 23-81-H3-36 | CRAH units Test & commission - Hall 3 | 1048100 | 0
137 | 23-21-H3-37 | Chilled water piping Install - Hall 3 | 586100 | 0
138 | 23-21-H3-38 | Chilled water piping Test & commission - Hall 3 | 735100 | 192800
139 | 25-10-H3-39 | Controls system Install - Hall 3 | 850300 | 0
140 | 25-10-H3-40 | Controls system Test & commission - Hall 3 | 891200 | 200600
141 | 25-30-H3-41 | PQ meters Install - Hall 3 | 463800 | 209100
142 | 25-30-H3-42 | PQ meters Test & commission - Hall 3 | 573100 | 0
143 | 01-10-00-43 | General conditions | 2100000 | 2100000