## Sheet
Line Ref | Item Description | Qty | Unit | Qty Installed | Pct
EL1-H01-2998 | Set Medium Voltage Equipment Lineup 1A | 2 | EA | 0 | 0
EL1-H01-002 | Terminate Medium Voltage Equipment Lineup 1A | 2 | EA | 0 | 0
EL1-H01-003 | Test Medium Voltage Equipment Lineup 1A | 2 | EA | 0 | 0
EL1-H01-004 | Set Medium Voltage Equipment Lineup 1B | 1 | EA | 0 | 0
EL1-H01-005 | Terminate Medium Voltage Equipment Lineup 1B | 6 | EA | 3.8 | 0.63
EL1-H01-006 | Test Medium Voltage Equipment Lineup 1B | 2 | EA | 0 | 0
EL1-H01-007 | Test Medium Voltage Equipment Lineup 1B | 6 | EA | 0 | 0
EL1-H01-008 | Terminate Medium Voltage Equipment Lineup 1C | 4 | EA | 3.1 | 0.765
EL1-H01-009 | Test Medium Voltage Equipment Lineup 1C | 2 | EA | 0.2 | 0.108
EL1-H01-010 | Set Medium Voltage Equipment Lineup 1D | 6 | EA | 0 | 0
EL1-H01-011 | Terminate Medium Voltage Equipment Lineup 1D | 1 | EA | 0 | 0
EL1-H01-012 | Test Medium Voltage Equipment Lineup 1D | 2 | EA | 0 | 0
EL1-H02-013 | Set Medium Voltage Equipment Lineup 2A | 4 | EA | 0 | 0
EL1-H02-014 | Terminate Medium Voltage Equipment Lineup 2A | 4 | EA | 0 | 0
EL1-H02-015 | Test Medium Voltage Equipment Lineup 2A | 6 | EA | 0 | 0
EL1-H02-016 | Set Medium Voltage Equipment Lineup 2B | 6 | EA | 0 | 0
EL1-H02-017 | Terminate Medium Voltage Equipment Lineup 2B | 6 | EA | 1.2 | 0.202
EL1-H02-018 | Test Medium Voltage Equipment Lineup 2B | 1 | EA | 0.4 | 0.406
EL1-H02-019 | Set Medium Voltage Equipment Lineup 2C | 1 | EA | 0 | 0
EL1-H02-020 | Terminate Medium Voltage Equipment Lineup 2C | 2 | EA | 0 | 0
EL1-H02-021 | Test Medium Voltage Equipment Lineup 2C | 4 | EA | 4 | 1
EL1-H02-022 | Set Medium Voltage Equipment Lineup 2D | 4 | EA | 2.2 | 0.542
EL1-H02-023 | Terminate Medium Voltage Equipment Lineup 2D | 4 | EA | 1.3 | 0.331
EL1-H02-024 |  | 4 | EA | 0 | 0
EL1-H03-025 | Set Medium Voltage Equipment Lineup 3A | 1 | EA | 0.1 | 0.051
EL1-H03-026 | Terminate Medium Voltage Equipment Lineup 3A | 1 | EA | 0.3 | 0.291
EL1-H03-2995 | Test Medium Voltage Equipment iLneup 3A | 4 | EA | 0 | 0
EL1-H03-2996 | Set Medium Voltage Equipment Lineup 3B | 1 | EA | 0.1 | 0.052
EL1-H03-2997 | Terminate Medium Voltage Equipment Lineup 3B | 6 | EA | 0 | 0
EL1-H03-030 | Test Medium Voltage Equipment Lineup 3B | 6 | EA | 3.9 | 0.648
EL1-H03-031 | Switchgear room lighting Hall 3 | 1 | EA | 0.4 | 0.438
EL1-H01-032 | UPS room receptacles Hall 1 | 1 | EA | 0.4 | 0.397