## Sheet
Line Ref | Item Description | Qty | Unit | Qty Installed | Pct
ME3-H01-001 | Set Cooling water mains Loop 1A | 1 | EA | 0.3 | 0.341
ME3-H01-002 | Connect Cooling water mains Loop 1A | 2 | EA | 0.4 | 0.177
ME3-H01-003 | Flush & start Cooling water mains Loop 1A | 1 | EA | 0 | 0
ME3-H01-004 | Set Cooling water mains Loop 1B | 2 | EA | 0 | 0
ME3-H01-005 | Connect Cooling water mains Loop 1B | 4 | EA | 0.9 | 0.225
ME3-H01-006 | Flush & start Cooling water mains Loop 1B | 1 | EA | 0 | 0
ME3-H01-007 | Set Cooling water mains Loop 1C | 4 | EA | 0 | 0
ME3-H01-008 | Connect Cooling water mains Loop 1C | 6 | EA | 0 | 0
ME3-H01-009 | Flush & start Cooling water mains Loop 1C | 4 | EA | 0.4 | 0.102
ME3-H01-010 | Set Cooling water mains Loop 1D | 2 | EA | 0 | 0
ME3-H01-011 | Connect Cooling water mains Loop 1D | 4 | EA | 0.5 | 12
ME3-H01-012 | Flush & start Cooling water mains Loop 1D | 1 | EA | 0.3 | 0.312
ME3-H02-013 | Set Cooling water mains Loop 2A | 1 | EA | 0 | 0
ME3-H02-014 | Connect Cooling water mains Loop 2A | 6 | EA | 3.3 | 0.553
ME3-H02-015 | Flush & start Cooling water mains Loop 2A | 1 | EA | 0.2 | 0.198
ME3-H02-016 | Set Cooling water mains Loop 2B | 4 | EA | 0 | 0
ME3-H02-017 | Connect Cooling water mains Loop 2B | 2 | EA | 0.7 | 0.354
ME3-H02-018 | Flush & start Cooling water mains Loop 2B | 6 | EA | 0.6 | 0.099
ME3-H02-019 | Set Cooling water mains Loop 2C | 2 | EA | 0.9 | 43
ME3-H02-020 | Connect Cooling water mains Loop 2C | 4 | EA | 0 | 0
ME3-H02-021 | Flush & start Cooling water mains Loop 2C | 6 | EA | 0.1 | 0.014
ME3-H02-022 | Set Cooling water mains Loop 2D | 2 | EA | 0 | 0
ME3-H02-023 | Connect Cooling water mains Loop 2D | 1 | EA | 0 | 0
ME3-H02-024 | Flush & star tCooling water mains Loop 2D | 6 | EA | 2.5 | 0.423
ME3-H03-025 | Set Cooling water mains Loop 3A | 4 | EA | 0 | 0
ME3-H03-026 | Connect Cooling water mains Loop 3A | 1 | EA | 0 | 0
ME3-H03-027 | Flush & start Cooling water mains Loop 3A | 2 | EA | 0 | 0
ME3-H03-028 | Set Cooling water mains Loop 3B | 1 | EA | 0.1 | 0.052
ME3-H03-029 | Connect Cooling water mains Loop 3B | 4 | EA | 0 | 0
ME3-H03-030 | Flush & start Cooling water mains Loop 3B | 2 | EA | 0.6 | 0.303
ME3-H03-031 | Set Cooling water mains Loop 3C | 1 | EA | 0.2 | 0.245
ME3-H03-032 | Connect Cooling water mains Loop 3C | 1 | EA | 0 | 0
ME3-H03-033 | Flush & start Cooling water mains Loop 3C | 2 | EA | 0.6 | 0.275