## Sheet
Line Ref | Item Description | Qty | Unit | Qty Installed | Pct
ME3-H01-001 | Set Cooling water mains Loop 1A | 1 | EA | 0.6 | 0.585
ME3-H01-002 | Connect Cooling water mains Loop 1A | 2 | EA | 0.7 | 0.369
ME3-H01-003 | Flush & start Cooling water mains Loop 1A | 1 | EA | 0.1 | 0.112
ME3-H01-004 | Set Cooling water mains Loop 1B | 2 | EA | 0 | 0
ME3-H01-005 | Connect Cooling water mainsL oop 1B | 4 | EA | 1.6 | 0.398
ME3-H01-006 | Flush & start Cooling water mains Loop 1B | 1 | EA | 0 | 0
ME3-H01-007 | Set Cooling water mains Loop 1C | 4 | EA | 0 | 0
ME3-H01-008 | Connect Cooling water mains Loop 1C | 6 | EA | 2.7 | 0.448
ME3-H01-009 | Flush &s tart Cooling water mains Loop 1C | 4 | EA | 1.4 | 0.342
ME3-H01-010 | Set Cooling water mains Loop 1D | 2 | EA | 0 | 0
ME3-H01-011 | Connect Cooling water mains Loop 1D | 4 | EA | 1.3 | 0.333
ME3-H01-012 | Flush & start Cooling water mains Loop 1D | 1 | EA | 0.8 | 0.751
ME3-H02-013 | Set Cooling water mains Loop 2A | 1 | EA | 0 | 0
ME3-H02-014 | Connect Cooling water mains Loop 2A | 6 | EA | 6 | 1
ME3-H02-015 | Flush & start Cooling water mains Loop 2A | 1 | EA | 0.5 | 0.452
ME3-H02-016 | Set Cooling water mains Loop 2B | 4 | EA | 0 | 0
ME3-H02-017 | Connect Cooling water mains Loop 2B | 2 | EA | 1.5 | 0.739
ME3-H02-018 | Flush & start Cooling water mains Loop 2B | 6 | EA | 2.5 | 0.416
ME3-H02-019 | Set Cooling water mains Loop 2C | 2 | EA | 1.6 | 0.809
ME3-H02-020 | Connect Cooling water mains Loop 2C | 4 | EA | 0.5 | 0.129
ME3-H02-021 | Flush & start Cooling water mains Loop 2C | 6 | EA | 3.1 | 0.512
ME3-H02-022 | Set Cooling water mains Loop 2D | 2 | EA | 0.3 | 0.131
ME3-H02-023 | Connect Cooling water mains Loop 2D | 1 | EA | 0 | 0
ME3-H02-4610 | Flush & start Cooling water mains Loop 2D | 6 | EA | 6 | 1
ME3-H03-025 | Set Cooling water mains Loop 3A | 4 | EA | 0 | 0
ME3-H03-026 | Connect Cooling water mains Loop 3A | 1 | EA | 0 | 0
ME3-H03-027 | Flush & start Cooling water mains Loop 3A | 2 | EA | 0 | 0
ME3-H03-028 | Set Cooling water mains Loop 3B | 1 | EA | 0.3 | 0.297
ME3-H03-4611 | Connect Cooling water mains Loop 3B | 4 | EA | 0 | 0
ME3-H03-030 | Flush & start Cooling water mains Loop 3B | 2 | EA | 1.6 | 0.786
ME3-H03-031 | Set Cooling water mains Loop 3C | 1 | EA | 0.8 | 0.768
ME3-H03-032 | Connect Cooling water mains Loop 3C | 1 | EA | 0.3 | 0.285
ME3-H03-033 | Flush & start Cooling water mains Loop 3C | 2 | EA | 1.3 | 0.655