## Sheet
Line No | Cost Code | Description of Work | Scheduled Value | Work Completed to Date
101 | 26-13-H1-1 | Switch Gear Install - Hall 1 | 858500 | 0
102 | 26-13-H1-2 | Switch Gear Test & commission - Hall 1 | 1015900 | 128900
103 | 26-33-H1-3 | Critical power modules Install - Hall 1 | 1996700 | 0
104 | 26-33-H1-4 | Critical power modules Test & commission - Hall 1 | 1141200 | 11200
105 | 26-25-H1-5 | Power track Install - Hall 1 | 1092100 | 369100
106 | 26-25-H1-6 | Power track Test & commission - Hall 1 | 587100 | 0
14758 | 23-81-H1-7 | Computer Room Air Handler Install - Hall 1 | 1550100 | 0
108 | 23-81-H1-8 | Computer Room Air Handler Test & commission - Hall 1 | 1047600 | 0
109 | 23-21-H1-9 | Process cooling water Install - Hall 1 | 2094000 | 0
110 | 23-21-H1-10 | Process cooling water Install - Hall 1 | 2237400 | 0
111 | 25-10-H1-11 | BMS Install - Hall 1 | 933800 | 0
112 | 25-10-H1-12 | BMS Test & commission - Hall 1 | 1540600 | 0
113 | 25-30-H1-13 | PQ meters Install - Hall 1 | 2027700 | 0
114 | 25-30-H1-14 | PQ meters Test & commission - Hall 1 | 1952700 | 0
115 | 26-13-H2-15 | Switch Gear Install - Hall 2 | 1134600 | 363700
116 | 26-13-H2-16 | Switch Gear Test & commission - Hall 2 | 903800 | 186300
117 | 26-33-H2-17 | Critical power modules Install - Hall 2 | 2326100 | 885800
14759 | 26-33-H2-18 | Critical power modules Test & commission - Hall 2 | 1272000 | 42900
119 | 26-25-H2-19 | Power track Install - Hall 2 | 204900 | 29600
14760 | 26-25-H2-20 | Power track Test & commission - Hall 2 | 208200 | 109000
121 | 23-81-H2-21 | Computer Room Air Handler Install - Hall 2 | 1074700 | 307700
122 | 23-81-H2-22 | Computer Room Air Handler Install - Hall 2 | 2031500 | 0
123 | 23-21-H2-23 | Process cooling water Install - Hall 2 | 815900 | 131600
124 | 23-21-H2-24 | Process cooling water Test & commission - Hall 2 | 839300 | 203300
125 | 25-10-H2-25 | BMS Install - Hall 2 | 1352300 | 0
126 | 25-10-H2-26 | BMS Test & commission - Hall 2 | 840700 | 0
127 | 25-30-H2-27 | PQ meters Install - Hall 2 | 2526700 | 655500
128 | 25-30-H2-28 | PQ meters Test & commission - Hall 2 | 1700800 | 806200
129 | 26-13-H3-29 | Switch Gear Install - Hall 3 | 817100 | 0
130 | 26-13-H3-30 | Switch Gear Test & commission - Hall 3 | 391200 | 0
131 | 26-33-H3-31 | Critical power modules Install - Hall 3 | 1441600 | 274300
132 | 26-33-H3-32 | Critical power modules Test & commission - Hall 3 | 2116500 | 164900
133 | 26-25-H3-33 | Power track Install - Hall 3 | 807300 | 0
134 | 26-25-H3-34 | Power track Test & commission - Hall 3 | 875500 | 0
135 | 23-81-H3-35 | Computer Room Air Handler Install - Hall 3 | 531800 | 0
136 | 23-81-H3-36 | Computer Room Air Handler Test & commission - Hall 3 | 554200 | 0
137 | 23-21-H3-37 | Process cooling water Install - Hall 3 | 1037400 | 0
138 | 23-21-H3-38 | Process cooling water Test & commission - Hall 3 | 1140600 | 0
139 | 25-10-H3-39 | BMS Install - Hall 3 | 2184100 | 1187900
140 | 25-10-H3-40 | BMS Test & commission - Hall 3 | 1703200 | 0
141 | 25-30-H3-41 | PQ meters Install - Hall 3 | 1212100 | 502800
142 | 25-30-H3-42 | PQ meters Test & commission - Hall 3 | 942400 | 0
143 | 01-10-00-43 | General conditions | 2100000 | 0