## START HERE
Northbank process expansion
UNAPPROVED · fictional source review · no professional decisions or approvals recorded
current source versions |  |  | unresolved versions |  | current target rows
13 |  |  | 3 |  | 12
OWNER WBS · relate the views, then inspect the source
I01.2.20 Electrical · possible connections
Schedule |  |  | Cost / forecast |  | Trade package
I-S03 · revision A I-S03 · revision B |  |  | I-C03 · revision A |  | I-P02 · revision A
I-S03 revision A: 30 September 2026. Proposed B: 15 October 2026. Confirm which revision applies; no approved delay is inferred.
Commissioning has schedule evidence but no supplied cost connection. CAD 700,000 unallocated contingency is a separate record.
Read all findings → |  |  | Inspect source records → |  | Open original sources →
Counting, authority and measurement →
Source type | Source versions | Original orientation |  | Review state | Source versions
schedule | 6 | WBS↔LINK / INDUSTRIAL-01 |  | Possible links | 10
cost | 4 | Entirely fictional private trial |  | Unresolved | 3
package | 3 | UNAPPROVED: no professional decisions or approvals recorded
Open Findings, then Crosswalk, then Sources.
Payment entitlement, installed progress and project health withheld.
Owner Code reading is a seeded synthetic fixture interpretation.
Same source projection as dashboard and management PDF.

## Findings
Finding / Overview | Management significance | Review request, not governed Action | Evidence
Two electrical finish dates need a decision. | Revision A states 30 September; proposed revision B states 15 October. Neither upload order nor a newer revision establishes professional approval. | Confirm the applicable schedule revision through the separate schedule approval workflow; retain both source assertions. | Baseline_Activity_Schedule.csv, row 4; Proposed_Phase2_Schedule_RevB.csv, row 2; Revision_Applicability_Notice.docx, paragraphs 2–3.
Electrical scope has a traceable starting point. | A supplied Owner Code connects electrical schedule, allowance or forecast, and trade records. This is a source-supported proposal, not an approved relationship. | Review the cited source records and confirm scope applicability before recording any professional decision. | Capex_Forecast_Register.csv, row 4; Baseline_Activity_Schedule.csv, row 4; Contractor_Package_Register.csv, row 3; Electrical_Switchgear_Specification.pdf, page 1.
Commissioning has schedule evidence, without cost allocation. | No supplied cost record names the commissioning Owner Code. Absence is not zero cost. Mixed package currencies prevent a defensible combined total. | Request the commissioning cost allocation and confirm currency and aggregation basis before management reporting. | Baseline_Activity_Schedule.csv, row 5; Capex_Forecast_Register.csv; Capital_Contract_Interfaces.pdf, page 1.
Keep unallocated contingency separate. | I-C04 records CAD 700,000 without an Owner Code. It is not a supplied commissioning cost forecast. | Confirm the contingency allocation separately from the missing commissioning cost relationship. | Capex_Forecast_Register.csv, row 5; Capital_Contract_Interfaces.pdf, page 1.

## Owner WBS
Owner Code / Overview | Name | Parent | Related source route / Overview
I01 | Northbank process expansion |  | Inspect first related source record →
I01.1 | Phase 1 / enabling | I01 | Inspect first related source record →
I01.1.10 | Civil works | I01.1 | Inspect first related source record →
I01.1.20 | Process equipment | I01.1 | Inspect first related source record →
I01.2 | Phase 2 / systems | I01 | Inspect first related source record →
I01.2.20 | Electrical | I01.2 | Inspect first related source record →
I01.2.30 | Automation | I01.2 | Inspect first related source record →
I01.3 | Phase 3 / start-up | I01 | Inspect first related source record →
I01.3.10 | Commissioning | I01.3 | Inspect first related source record →

## Crosswalk
Stable source version ID | Source record / Overview | Source file | Locator | Source role | Original assertion | Candidate targets, NOT APPROVED | Disposition | Engine outcome | Recorded basis | Contrary evidence | Revision | Professional decision | Whole-version approval
INDUSTRIAL-01-Baseline_Activity_Schedule.csv-I-S01 | I-S01 | Baseline_Activity_Schedule.csv | row 2 | schedule | Record ID: I-S01 ¦ Owner Code: I01.1.10 ¦ Description: Prepare process foundations ¦ Trade: Granite Civil ¦ Phase: Phase 1 ¦ Start: 2026-06-01 ¦ Finish: 2026-07-05 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion | I01.1.10 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Baseline_Activity_Schedule.csv-I-S02 | I-S02 | Baseline_Activity_Schedule.csv | row 3 | schedule | Record ID: I-S02 ¦ Owner Code: I01.1.20 ¦ Description: Set process equipment ¦ Trade: Forge Mechanical ¦ Phase: Phase 1 ¦ Start: 2026-07-06 ¦ Finish: 2026-08-20 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion | I01.1.20 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Baseline_Activity_Schedule.csv-I-S03 | I-S03 | Baseline_Activity_Schedule.csv | row 4 | schedule | Record ID: I-S03 ¦ Owner Code: I01.2.20 ¦ Description: Energize electrical distribution ¦ Trade: Vector Power ¦ Phase: Phase 2 ¦ Start: 2026-09-01 ¦ Finish: 2026-09-30 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion | I01.2.20 | Unresolved | AUTO | assigned | Competing source revisions; applicability and separate schedule approval are unresolved. Both source assertions are retained. | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Baseline_Activity_Schedule.csv-I-S04 | I-S04 | Baseline_Activity_Schedule.csv | row 5 | schedule | Record ID: I-S04 ¦ Owner Code: I01.3.10 ¦ Description: Integrated commissioning ¦ Trade: Start-up team ¦ Phase: Phase 3 ¦ Start: 2026-10-15 ¦ Finish: 2026-11-15 ¦ Amount: ¦ Currency: ¦ Revision: A ¦ Status: Source assertion | I01.3.10 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Capex_Forecast_Register.csv-I-C01 | I-C01 | Capex_Forecast_Register.csv | row 2 | cost | Record ID: I-C01 ¦ Owner Code: I01.1.10 ¦ Description: Civil capital forecast ¦ Trade: Granite Civil ¦ Phase: Phase 1 ¦ Start: ¦ Finish: ¦ Amount: 1900000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion | I01.1.10 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Capex_Forecast_Register.csv-I-C02 | I-C02 | Capex_Forecast_Register.csv | row 3 | cost | Record ID: I-C02 ¦ Owner Code: I01.1.20 ¦ Description: Equipment capital forecast ¦ Trade: Forge Mechanical ¦ Phase: Phase 1 ¦ Start: ¦ Finish: ¦ Amount: 4600000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion | I01.1.20 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Capex_Forecast_Register.csv-I-C03 | I-C03 | Capex_Forecast_Register.csv | row 4 | cost | Record ID: I-C03 ¦ Owner Code: I01.2.20 ¦ Description: Electrical capital forecast ¦ Trade: Vector Power ¦ Phase: Phase 2 ¦ Start: ¦ Finish: ¦ Amount: 2200000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion | I01.2.20 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Capex_Forecast_Register.csv-I-C04 | I-C04 | Capex_Forecast_Register.csv | row 5 | cost | Record ID: I-C04 ¦ Owner Code: ¦ Description: Unallocated owner contingency ¦ Trade: ¦ Phase: All phases ¦ Start: ¦ Finish: ¦ Amount: 700000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion |  | Unresolved | NEW_SCOPE | confident_facet_no_matching_node | SCOPE_NATURE='RESERVE' matches no node in the project WBS | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Contractor_Package_Register.csv-I-P01 | I-P01 | Contractor_Package_Register.csv | row 2 | package | Record ID: I-P01 ¦ Owner Code: I01.1.20 ¦ Description: Process equipment package ¦ Trade: Forge Mechanical ¦ Phase: Phase 1 ¦ Start: ¦ Finish: ¦ Amount: 1200000 ¦ Currency: USD ¦ Revision: A ¦ Status: Source assertion | I01.1.20 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Contractor_Package_Register.csv-I-P02 | I-P02 | Contractor_Package_Register.csv | row 3 | package | Record ID: I-P02 ¦ Owner Code: I01.2.20 ¦ Description: Electrical installation package ¦ Trade: Vector Power ¦ Phase: Phase 2 ¦ Start: ¦ Finish: ¦ Amount: 1600000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion | I01.2.20 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Contractor_Package_Register.csv-I-P03 | I-P03 | Contractor_Package_Register.csv | row 4 | package | Record ID: I-P03 ¦ Owner Code: I01.2.30 ¦ Description: Automation package ¦ Trade: Signal Works ¦ Phase: Phase 2 ¦ Start: ¦ Finish: ¦ Amount: 900000 ¦ Currency: CAD ¦ Revision: A ¦ Status: Source assertion | I01.2.30 | Source-aligned proposal | AUTO | assigned |  | A | No decision recorded | No approval recorded
INDUSTRIAL-01-Proposed_Phase2_Schedule_RevB.csv-I-S03 | I-S03 | Proposed_Phase2_Schedule_RevB.csv | row 2 | schedule | Record ID: I-S03 ¦ Owner Code: I01.2.20 ¦ Description: Energize electrical distribution ¦ Trade: Vector Power ¦ Phase: Phase 2 ¦ Start: 2026-09-15 ¦ Finish: 2026-10-15 ¦ Amount: ¦ Currency: ¦ Revision: B ¦ Status: Proposed, not approved | I01.2.20 | Unresolved | AUTO | assigned | Competing source revisions; applicability and separate schedule approval are unresolved. Both source assertions are retained. | B | No decision recorded | No approval recorded
INDUSTRIAL-01-Proposed_Phase2_Schedule_RevB.csv-I-S05 | I-S05 | Proposed_Phase2_Schedule_RevB.csv | row 3 | schedule | Record ID: I-S05 ¦ Owner Code: I01.2.30 ¦ Description: Controls integration ¦ Trade: Signal Works ¦ Phase: Phase 2 ¦ Start: 2026-10-05 ¦ Finish: 2026-10-25 ¦ Amount: ¦ Currency: ¦ Revision: B ¦ Status: Proposed, not approved | I01.2.30 | Source-aligned proposal | AUTO | assigned |  | B | No decision recorded | No approval recorded

## Sources
Source file / Overview | Classified by content | SHA-256 | Bytes | Extracted blocks
Baseline_Activity_Schedule.csv | schedule | 152dc98bc6f04093691a5f91a209c5730f004858312e00de200b133018939406 | 525 | 4
Capex_Forecast_Register.csv | cost | 45c9e7b6362bfda3c926f400cb1067a48519a74d468d28fb89d30ce33673fb90 | 466 | 4
Capital_Contract_Interfaces.pdf | contract | 529b7f9bb18d8d44cf328e1b6447574a87afc0aa12f1a76bedb27d0fa4222745 | 19663 | 11
Contractor_Package_Register.csv | package | 51d0a6980ad1b7a512cd904fafd7f335bffcfea57cdc116841ffba7297b887fd | 381 | 3
Electrical_Switchgear_Specification.pdf | specification | ace9f2813f527d5ba0c13296502918de2faad0e2743c88a98fd6219039843386 | 19564 | 10
Owner_Scope_Register.csv | Owner WBS | 835440e27805fcda8d9512e63a5ad3bcbc369ea2febd92f543a71db440530734 | 293 | 9
Proposed_Phase2_Schedule_RevB.csv | schedule | e8c6b6dcafb0dff48bd19064268af43dd39c5ae5b58ac4a5bc71c154fdce2261 | 321 | 2
Revision_Applicability_Notice.docx | review note | 75e0007913f0237f0a7e715e70b11fd4eba2a0811e69d0abbb648a4a70b8443d | 1003 | 4

## Measurement
Measure / Overview | Value / boundary
elapsed_seconds | 0.014574
cpu_seconds | 0.014585
peak_process_rss_mib | 64.2422
files | 8
records | 13
supported_proposals | 10
abstentions | 3
measurement_boundary | Measured Python source parsing and evidence evaluation, shared Linux process; peak RSS is cumulative process high-water mark, not incremental case memory or browser memory. Export generation excluded.
energy | Not measured
carbon | Not measured
external_models | Not tested; no paid API or external model calls.